## Transformed by JSON-CSV.COM
SL | Module | Test Case ID | Scenario ID | Test Cycle | Expected Result | User | Execution Date | Actual Result | Failure Justification | Defect No | Log Date | Severity | Details | Status | Defect Owner | Closing Date
1 | Core HR | HR001 | HR001-1 | 1 | Pass | Amit | 20-05-2019 | Fail |  | HR001-1-1 | 20-05-1992 | Critical | xyz | Open | Amit
2 | Core HR | HR001 | HR001-2 | 1 | Fail | Suzi | 20-05-2019 | Fail
3 | Core HR | HR001 | HR001-3 | 1 | Fail | Bruce | 20-05-2019 | Fail
4 | Core HR | HR001 | HR001-4 | 1 | Fail | Mary | 20-05-2019 | Fail
5 | Core HR | HR001 | HR001-5 | 1 | Fail | Wendy | 20-05-2019 | Fail
6 | Core HR | HR002 | HR002-1 | 1 | Pass | Jake | 20-05-2019 | Pass
7 | Core HR | HR002 | HR002-2 | 1 | Fail | Suzi | 20-05-2019 | Fail
8 | Core HR | HR002 | HR002-3 | 1 | Fail | Bruce | 20-05-2019 | Fail
9 | Core HR | HR003 | HR003-1 | 1 | Pass | Mary | 20-05-2019 | Pass
10 | Core HR | HR004 | HR004-1 | 1 | Pass | Amit | 20-05-2019 | Fail |  | HR004-1-10 | 20-05-1992 | High | abc | Open | Amit
11 | Core HR | HR003 | HR003-1 | 2 | Pass | Amit | 20-05-2019 | Pass |  |  |  | High | abc | Open | Amit
12 | Core HR | HR003 | HR003-2 | 1 | Pass | Amit | 20-05-2019 | Pass |  |  |  | Medium | abc | Open | Amit
13 | Core HR | HR003 | HR003-1 | 3 | Pass | Amit | 24-05-2019 | Pass |  |  |  | High | abc | Open | Amit
14 | Core HR | HR001 | HR001-1 | 2 | Pass | Amit | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Amit
15 | Core HR | HR001 | HR001-2 | 2 | Fail | Amit | 27-05-2019 | Fail
16 | Core HR | HR001 | HR001-3 | 2 | Fail | Amit | 27-05-2019 | Fail
17 | Core HR | HR001 | HR001-4 | 2 | Fail | Amit | 27-05-2019 | Fail
18 | Core HR | HR001 | HR001-5 | 2 | Fail | Amit | 27-05-2019 | Fail
19 | Core HR | HR002 | HR002-1 | 2 | Pass | Arup | 27-05-2019 | Fail |  | HR002-1-19 | 27-05-2019 | Low | abc | Open | Amit
20 | Core HR | HR002 | HR002-2 | 2 | Fail | Arup | 27-05-2019 | Fail
21 | Core HR | HR002 | HR002-3 | 2 | Fail | Arup | 27-05-2019 | Pass
22 | Core HR | HR002 | HR002-4 | 1 | Fail | Sumit | 27-05-2019 | Fail
23 | Core HR | HR002 | HR002-5 | 1 | Fail | Sumit | 27-05-2019 | Fail
24 | Core HR | HR004 | HR004-1 | 2 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-1-24 | 27-05-2019 | High | abc | Open | Amit
25 | Core HR | HR004 | HR004-2 | 1 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-2-25 | 27-05-2019 | High | abc | Open | Amit
26 | Core HR | HR004 | HR004-3 | 1 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-3-26 | 27-05-2019 | Low | abc | Open | Sumit
27 | Core HR | HR001 | HR001-1 | 3 | Pass | Sumit | 27-05-2019 | Pass
28 | Core HR | HR001 | HR001-2 | 3 | Fail | Sumit | 27-05-2019 | Fail
29 | Core HR | HR001 | HR001-3 | 3 | Pass | Sumit | 27-05-2019 | Fail |  | HR001-3-29 | 27-05-2019 | High | abc | Open | Sumit
30 | Core HR | HR001 | HR001-4 | 3 | Fail | Arup | 27-05-2019 | Fail
31 | Core HR | HR001 | HR001-5 | 3 | Pass | Arup | 27-05-2019 | Fail |  | HR001-5-31 | 27-05-2019 | High | abc | Open | Sumit
32 | Core HR | HR002 | HR002-1 | 3 | Pass | Alish | 27-05-2019 | Pass
33 | Core HR | HR002 | HR002-2 | 3 | Fail | Alish | 27-05-2019 | Fail
34 | Core HR | HR002 | HR002-3 | 3 | Pass | Alish | 27-05-2019 | Fail |  | HR002-3-34 | 27-05-2019 | Medium | abc | Open | Sumit
35 | Core HR | HR002 | HR002-4 | 2 | Fail | Alish | 27-05-2019 | Fail
36 | Core HR | HR002 | HR002-5 | 2 | Pass | Alish | 27-05-2019 | Fail |  | HR002-5-36 | 27-05-2019 | High | abc | Open | Sumit
37 | Core HR | HR004 | HR004-1 | 3 | Pass | Alish | 27-05-2019 | Fail |  | HR004-1-37 | 27-05-2019 | High | abc | Open | Sumit
38 | Core HR | HR004 | HR004-2 | 2 | Pass | Super User | 27-05-2019 | Pass
39 | Core HR | HR004 | HR004-3 | 2 | Pass | Alish | 27-05-2019 | Fail |  | HR004-3-39 | 27-05-2019 | High | abc | Open | Sumit
40 | Payroll | HR001 | HR001-1 | 1 | Pass | Alish | 27-05-2019 | Fail |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Jade
41 | Payroll | HR004 | HR004-1 | 1 | Pass | Alish | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Arup
42 | Payroll | HR001 | HR001-1 | 2 | Pass | Alish | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Arup
43 | Payroll | HR004 | HR004-3 | 1 | Pass | Alish | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Arup
44 | Payroll | HR002 | HR002-3 | 1 | Pass | Alish | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Arup
45 | Payroll | HR001 | HR001-1 | 3 | Pass | Alish | 27-05-2019 | Pass |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Arup
46 | Payroll | HR004 | HR004-1 | 2 | Pass | Alish | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Debashish
47 | Payroll | HR001 | HR001-1 | 4 | Pass | Arup | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Debashish
48 | Payroll | HR004 | HR004-3 | 2 | Pass | Arup | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Debashish
49 | Payroll | HR002 | HR002-3 | 2 | Pass | Arup | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Debashish
50 | Payroll | HR001 | HR001-1 | 5 | Pass | Arup | 27-05-2019 | Fail |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Debashish
51 | Payroll | HR004 | HR004-1 | 3 | Pass | Arup | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Debashish
52 | Payroll | HR001 | HR001-1 | 6 | Pass | Arup | 27-05-2019 | Pass |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Debashish
53 | Payroll | HR004 | HR004-3 | 3 | Pass | Arup | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Debashish
54 | Payroll | HR002 | HR002-3 | 3 | Pass | Arup | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Debashish
55 | Benefits | HR001 | HR001-1 | 1 | Pass | Arup | 27-05-2019 | Fail |  | HR001-1-45 | 27-05-2019 | Critical | xyz | Open | Debashish
56 | Benefits | HR004 | HR004-1 | 1 | Pass | Arup | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | Critical | abc | Open | Alish
57 | Benefits | HR001 | HR001-1 | 2 | Pass | Arup | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Alish
58 | Benefits | HR004 | HR004-3 | 1 | Pass | Arup | 27-05-2019 | Fail |  | HR004-3-48 | 27-05-2019 | Low | abc | Open | Alish
59 | Benefits | HR002 | HR002-3 | 1 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Medium | abc | Open | Alish
60 | Benefits | HR002 | HR002-3 | 2 | Pass | Sumit | 27-05-2019 | Pass |  | HR002-3-49 | 27-05-2019 | Low | abc | Open | Alish
61 | Benefits | HR001 | HR001-1 | 3 | Pass | Sumit | 27-05-2019 | Fail |  | HR001-1-45 | 27-05-2019 | Critical | xyz | Open | Alish
62 | Benefits | HR004 | HR004-1 | 2 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | Critical | abc | Open | Alish
63 | Benefits | HR001 | HR001-1 | 4 | Pass | Sumit | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Alish
64 | Benefits | HR004 | HR004-3 | 2 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-3-48 | 27-05-2019 | Low | abc | Open | Alish
65 | Benefits | HR002 | HR002-3 | 3 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Medium | abc | Open | Alish
66 | Benefits | HR002 | HR002-3 | 4 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Low | abc | Open | Alish
67 | Benefits | HR001 | HR001-1 | 5 | Pass | Sumit | 27-05-2019 | Pass |  | HR001-1-45 | 27-05-2019 | Critical | xyz | Open | Alish
68 | Benefits | HR004 | HR004-1 | 3 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | Critical | abc | Open | Anurag
69 | Benefits | HR001 | HR001-1 | 6 | Pass | Sumit | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Anurag
70 | Benefits | HR004 | HR004-3 | 3 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-3-48 | 27-05-2019 | Low | abc | Open | Anurag
71 | Benefits | HR002 | HR002-3 | 5 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Medium | abc | Open | Anurag
72 | Benefits | HR002 | HR002-3 | 6 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Low | abc | Open | Anurag
73 | Payroll | HR001 | HR001-1 | 7 | Pass | Sumit | 27-05-2019 | Pass |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Anurag
74 | Payroll | HR004 | HR004-1 | 4 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Anurag
75 | Payroll | HR001 | HR001-1 | 8 | Pass | Sumit | 27-05-2019 | Pass |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Anurag
76 | Payroll | HR004 | HR004-3 | 4 | Pass | Sumit | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Harsh
77 | Payroll | HR002 | HR002-3 | 4 | Pass | Sumit | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Harsh
78 | Benefits | HR001 | HR001-1 | 7 | Pass | Sumit | 27-05-2019 | Fail |  | HR001-1-45 | 27-05-2019 | Critical | xyz | Open | Harsh
79 | Benefits | HR004 | HR004-1 | 4 | Pass | Wendy | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | Critical | abc | Open | Harsh
80 | Benefits | HR001 | HR001-1 | 8 | Pass | Anurag | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Harsh
81 | Benefits | HR004 | HR004-3 | 4 | Pass | Anurag | 27-05-2019 | Fail |  | HR004-3-48 | 27-05-2019 | Low | abc | Open | Harsh
82 | Benefits | HR002 | HR002-3 | 7 | Pass | Anurag | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Medium | abc | Open | Harsh
83 | Benefits | HR002 | HR002-3 | 8 | Pass | Anurag | 27-05-2019 | Fail |  | HR002-3-49 | 27-05-2019 | Low | abc | Open | Harsh
84 | Core HR | HR001 | HR001-1 | 4 | Pass | Anurag | 20-05-2019 | Fail |  | HR001-1-1 | 20-05-1992 | Critical | xyz | Open | Harsh
85 | Core HR | HR001 | HR001-1 | 5 | Pass | Anurag | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Rajat
86 | Core HR | HR001 | HR001-1 | 6 | Pass | Super User | 27-05-2019 | Pass
87 | Core HR | HR001 | HR001-1 | 7 | Pass | Anurag | 20-05-2019 | Fail |  | HR001-1-1 | 20-05-1992 | Critical | xyz | Open | Rajat
88 | Core HR | HR001 | HR001-1 | 8 | Pass | Anurag | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Rajat
89 | Core HR | HR002 | HR002-2 | 4 | Fail | Suzi | 20-05-2019 | Fail
90 | Core HR | HR002 | HR002-2 | 5 | Fail | Super User | 27-05-2019 | Fail
91 | Core HR | HR002 | HR002-2 | 6 | Fail | Super User | 27-05-2019 | Fail
92 | Core HR | HR002 | HR002-2 | 7 | Fail | Suzi | 20-05-2019 | Fail
93 | Core HR | HR002 | HR002-2 | 8 | Fail | Super User | 27-05-2019 | Fail
94 | Core HR | HR002 | HR002-3 | 4 | Fail | Bruce | 20-05-2019 | Fail
95 | Core HR | HR002 | HR002-3 | 5 | Fail | Super User | 27-05-2019 | Fail
96 | Core HR | HR002 | HR002-3 | 6 | Pass | Anurag | 27-05-2019 | Fail |  | HR002-3-34 | 27-05-2019 | Medium | abc | Open | Rajat
97 | Core HR | HR002 | HR002-3 | 7 | Fail | Bruce | 20-05-2019 | Fail
98 | Core HR | HR002 | HR002-3 | 8 | Fail | Super User | 27-05-2019 | Fail
99 | Reporting | HR001 | HR001-1 | 1 | Pass | Anurag | 27-05-2019 | Fail |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Rajat
100 | Reporting | HR004 | HR004-1 | 1 | Pass | Anurag | 27-05-2019 | Pass |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Rajat
101 | Reporting | HR001 | HR001-1 | 2 | Pass | Debashish | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Rajat
102 | Reporting | HR004 | HR004-3 | 1 | Pass | Debashish | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Rajat
103 | Reporting | HR002 | HR002-3 | 1 | Pass | Debashish | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Rajat
104 | Reporting | HR001 | HR001-1 | 3 | Pass | Debashish | 27-05-2019 | Fail |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Rajat
105 | Reporting | HR004 | HR004-1 | 2 | Pass | Debashish | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Rajat
106 | Reporting | HR001 | HR001-1 | 4 | Pass | Anurag | 27-05-2019 | Pass |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Rajat
107 | Reporting | HR004 | HR004-3 | 2 | Pass | Anurag | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Rajat
108 | Reporting | HR002 | HR002-3 | 2 | Pass | Anurag | 27-05-2019 | Fail |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Arup
109 | Reporting | HR001 | HR001-1 | 5 | Pass | Debashish | 27-05-2019 | Fail |  | HR001-1-40 | 27-05-2019 | Critical | xyz | Open | Arup
110 | Reporting | HR004 | HR004-1 | 3 | Pass | Debashish | 27-05-2019 | Fail |  | HR004-1-10 | 27-05-2019 | High | abc | Open | Arup
111 | Reporting | HR001 | HR001-1 | 6 | Pass | Debashish | 27-05-2019 | Pass |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Arup
112 | Reporting | HR004 | HR004-3 | 3 | Pass | Debashish | 27-05-2019 | Fail |  | HR004-3-43 | 27-05-2019 | Low | abc | Open | Arup
113 | Reporting | HR002 | HR002-3 | 3 | Pass | Debashish | 27-05-2019 | Pass |  | HR002-3-44 | 27-05-2019 | Medium | abc | Open | Arup