## Execution Details
SL | Module | Test Case ID | Scenario ID | Test Cycle | Expected Result | User | Execution Date | Actual Result | Failure Justification | Defect No | Log Date | Severity | Details | Status | Defect Owner | Closing Date
1 | Core HR | HR001 | HR001-1 | 1 | Pass | Jake | 2019-05-20 | Fail |  | HR001-1-1 | 2019-05-20 | Critical | xyz | Open | Jade
2 | Core HR | HR001 | HR001-2 | 1 | Fail | Suzi | 2019-05-20 | Fail
3 | Core HR | HR001 | HR001-3 | 1 | Fail | Bruce | 2019-05-20 | Fail
4 | Core HR | HR001 | HR001-4 | 1 | Fail | Mary | 2019-05-20 | Fail
5 | Core HR | HR001 | HR001-5 | 1 | Fail | Wendy | 2019-05-20 | Fail
6 | Core HR | HR002 | HR002-1 | 1 | Pass | Jake | 2019-05-20 | Pass
7 | Core HR | HR002 | HR002-2 | 1 | Fail | Suzi | 2019-05-20 | Fail
8 | Core HR | HR002 | HR002-3 | 1 | Fail | Bruce | 2019-05-20 | Fail
9 | Core HR | HR003 | HR003-1 | 1 | Pass | Mary | 2019-05-20 | Pass
10 | Core HR | HR004 | HR004-1 | 1 | Pass | Wendy | 2019-05-20 | Fail |  | HR004-1-10 | 2019-05-20 | High | abc | Open | Garett
11 | Core HR | HR003 | HR003-1 | 2 | Pass | Super User | 2019-05-20 | Pass |  |  |  | High | abc | Open | Garett
12 | Core HR | HR003 | HR003-2 | 1 | Pass | Super User | 2019-05-20 | Pass |  |  |  | Medium | abc | Open | Garett
13 | Core HR | HR003 | HR003-1 | 3 | Pass | Super User | 24-05-2019 | Pass |  |  |  | High | abc | Open | Garett
14 | Core HR | HR001 | HR001-1 | 2 | Pass | Super User | 27-05-2019 | Fail |  | HR001-1-14 | 27-05-2019 | High | abc | Open | Garett
15 | Core HR | HR001 | HR001-2 | 2 | Fail | Super User | 27-05-2019 | Fail
16 | Core HR | HR001 | HR001-3 | 2 | Fail | Super User | 27-05-2019 | Fail
17 | Core HR | HR001 | HR001-4 | 2 | Fail | Super User | 27-05-2019 | Fail
18 | Core HR | HR001 | HR001-5 | 2 | Fail | Super User | 27-05-2019 | Fail
19 | Core HR | HR002 | HR002-1 | 2 | Pass | Super User | 27-05-2019 | Fail |  | HR002-1-19 | 27-05-2019 | Low | abc | Open | Garett
20 | Core HR | HR002 | HR002-2 | 2 | Fail | Super User | 27-05-2019 | Fail
21 | Core HR | HR002 | HR002-3 | 2 | Fail | Super User | 27-05-2019 | Fail
22 | Core HR | HR002 | HR002-4 | 1 | Fail | Super User | 27-05-2019 | Fail
23 | Core HR | HR002 | HR002-5 | 1 | Fail | Super User | 27-05-2019 | Fail
24 | Core HR | HR004 | HR004-1 | 2 | Pass | Super User | 27-05-2019 | Fail |  | HR004-1-24 | 27-05-2019 | High | abc | Open | Garett
25 | Core HR | HR004 | HR004-2 | 1 | Pass | Super User | 27-05-2019 | Fail |  | HR004-2-25 | 27-05-2019 | High | abc | Open | Garett
26 | Core HR | HR004 | HR004-3 | 1 | Pass | Super User | 27-05-2019 | Fail |  | HR004-3-26 | 27-05-2019 | Low | abc | Open | Garett
27 | Core HR | HR001 | HR001-1 | 3 | Pass | Super User | 27-05-2019 | Pass
28 | Core HR | HR001 | HR001-2 | 3 | Fail | Super User | 27-05-2019 | Fail
29 | Core HR | HR001 | HR001-3 | 3 | Pass | Super User | 27-05-2019 | Fail |  | HR001-3-29 | 27-05-2019 | High | abc | Open | Garett
30 | Core HR | HR001 | HR001-4 | 3 | Fail | Super User | 27-05-2019 | Fail
31 | Core HR | HR001 | HR001-5 | 3 | Pass | Super User | 27-05-2019 | Fail |  | HR001-5-31 | 27-05-2019 | High | abc | Open | Garett
32 | Core HR | HR002 | HR002-1 | 3 | Pass | Super User | 27-05-2019 | Pass
33 | Core HR | HR002 | HR002-2 | 3 | Fail | Super User | 27-05-2019 | Fail
34 | Core HR | HR002 | HR002-3 | 3 | Pass | Super User | 27-05-2019 | Fail |  | HR002-3-34 | 27-05-2019 | Medium | abc | Open | Garett
35 | Core HR | HR002 | HR002-4 | 2 | Fail | Super User | 27-05-2019 | Fail
36 | Core HR | HR002 | HR002-5 | 2 | Pass | Super User | 27-05-2019 | Fail |  | HR002-5-36 | 27-05-2019 | High | abc | Open | Garett
37 | Core HR | HR004 | HR004-1 | 3 | Pass | Super User | 27-05-2019 | Fail |  | HR004-1-37 | 27-05-2019 | High | abc | Open | Garett
38 | Core HR | HR004 | HR004-2 | 2 | Pass | Super User | 27-05-2019 | Pass
39 | Core HR | HR004 | HR004-3 | 2 | Pass | Super User | 27-05-2019 | Fail |  | HR004-3-39 | 27-05-2019 | High | abc | Open | Garett
Formulas:
Log Date = IF([Actual Result]<>[Expected Result],[Execution Date],"")